## Project Name - Thirsty Wine
Project Name :- Thirsty Wine
TEST SCENERIO & TEST CASES

## Test Scenario
Test Scenario
Project Name |  | Thirsty Wine
Client |  | Thirsty Wine
Created By |  | Vikas Sahani, Atul Pal
Creation Date |  | 2025-02-06
Approval By |  | Masai
Approval Date |  | 2025-02-06
Test Scenario ID | Test Scenario | Priority | Number of Test Cases | Passed Test Cases | Failed Test Cases
TS_001 | Validate the 'User Register' functionality | P1 | 6 | 2 | 4
TS_002 | Validate the 'User Login' functionality | P1 | 5 | 5 | 0
TS_003 | Validate the 'Admin Register' functionality | P1 | 6 | 2 | 4
TS_004 | Validate the 'Admin Login' functionality | P1 | 5 | 5 | 0
TS_005 | Validate the 'Admin Dashboard' functionality | P1 | 5 | 4 | 1
TS_006 | Validate the 'Search' functionality | P1 | 8 | 2 | 6
TS_007 | Validate the 'Cart' functionality | P1 | 10 | 9 | 1
TS_008 | Validate the 'Checkout' functionality | P1 | 22 | 11 | 11
TS_009 | Validate the 'Product Page' functionality | P1 | 5 | 5 | 0
TS_010 | Validate the 'Catlog Filter and Shorting' functionality | P1 | 14 | 12 | 2
TS_011 | Validate the 'Wishlist ' functionality | P1 | 5 | 5 | 0
TS_012 | Validate UI and Non-Functionality testing | P1 | 10 | 8 | 2
Total Test Cases |  |  | 101 | 70 | 31

## User Register
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-Conditions | Test-Steps | Test Data | Expected Result | Actual Result | Status
TS_001 | Validate the 'User Register' functionality | TC_001 | Validate user can Register with valid details | 1.Good internet 2.Laptop 3.URL :- https://pay-pal-pioneers-068.vercel.app/ 4.Browser :- Chrome-131 5.User on the Login page | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "12345" into "Password*" 6. Select Role "User" 7. Click Register Button | Name - vikas sahani Email - vikas1@gmail.com Password - 12345 Role - User | User is registered successfully | As Expected | Pass
|  | TC_002 | Validate Register a user with invalid email format |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "45@gl.com" into "Email*" 5. Enter "12345" into "Password*" 6. Select Role "User" 7. Click Register Button | Name - vikas sahani Email - 45@gl.com Password - 12345 Role - User | - An error message is displayed: "Invalid email format. Please enter a valid email." | As Expected | Fail
|  | TC_003 | Validate user Register with an already registered email |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "12345" into "Password*" 6. Select Role "User" 7. Click Register Button | Enter "vikas sahani" into "Name*" Enter "vikas1@gmail.com" into "Email*" Enter "12345" into "Password*" Select Role "User" | User already registered | User is registered successfully | Fail
|  | TC_004 | Register with missing mandatory fields |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "12345" into "Password*" 5. Select Role "User" 6. Click Register Button | Enter "vikas sahani" into "Name*" Enter "12345" into "Password*" Select Role "User" | Error message shows fill the input form | As Expected | Pass
|  | TC_005 | Register a user with invalid Password format |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "1" into "Password*" 6. Select Role "User" 7. Click Register Button | Enter "vikas sahani" into "Name*" Enter "vikas1@gmail.com" into "Email*" Enter "1" into "Password*" Select Role "User" | Enter the valid password | User is registered successfully | Fail
|  | TC_006 | Register a user with invalid Name format |  | 1. Open website 2. Click on "Sign Up" 3. Enter "1" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "1" into "Password*" 6. Select Role "User" 7. Click Register Button | Enter "1" into "Name*" Enter "vikas1@gmail.com" into "Email*" Enter "1" into "Password*" Select Role "User" | Give an error message | User is registered successfully | Fail

## User Login
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-Conditions | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_002 | Validate the 'User Login' functionality | TC_001 | Validater user Login with valid credentials | 1.Good internet 2.Laptop 3.URL : - https://pay-pal-pioneers-068.vercel.app/ 4.Browser :- Chrome-131 5.User on the Login page | 1. Open website 2. Click on "Login" 3. Enter the data | Enter "vikas1@gmail.com" into "Email*" Enter "12345" into "Password*" | User login successfully | As Expected | Pass
|  | TC_002 | Validater user Login with invalid credentials |  | 1. Open website 2. Click on "Login" 3. Enter the data | Enter "vikas1@gmail.com" into "Email*" Enter "1ddd" into "Password*" | User unable to login | As Expected | Pass
|  | TC_003 | Validate user Login with blank fields |  | 1. Open website 2. Click on "Login" 3. Enter the data | NA | Error message show | As Expected | Pass
|  | TC_004 | Validate user Login without enter Password |  | 1. Open website 2. Click on "Login" 3. Enter the data | Enter "vikas1@gmail.com" into "Email*" | Error message show | As Expected | Pass
|  | TC_005 | Validate user Login without enter Email |  | 1. Open website 2. Click on "Login" 3. Enter the data | Enter "12345" into "Password*" | Error message show | As Expected | Pass

## Admin Register
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-Conditions | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_003 | Validate the 'Admin Register' functionality | TC_001 | Validate Admin can Register with valid details As a Admin | 1.Good internet 2.Laptop 3.URL : - https://pay-pal-pioneers-068.vercel.app/ 4.Browser :- Chrome-131 5.Admin on the Login page | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "12345" into "Password*" 6. Select Role "Admin" 7. Click Register Button | Name - vikas sahani Email - vikas1@gmail.com Password - 12345 Role - Admin | Admin is registered successfully | As Expected | Pass
|  | TC_002 | Validate the 'Admin Register' functionality |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "45@gl.com" into "Email*" 5. Enter "12345" into "Password*" 6. Select Role "Admin" 7. Click Register Button | Name - vikas sahani Email - 45@gl.com Password - 12345 Role - Admin | - An error message is displayed: "Invalid email format. Please enter a valid email." | As Expected | Fail
|  | TC_003 | Validate Admin Register with an already registered email |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "12345" into "Password*" 6. Select Role "Admin" 7. Click Register Button | Enter "vikas sahani" into "Name*" Enter "vikas1@gmail.com" into "Email*" Enter "12345" into "Password*" Select Role "Admin" | Admin already registered | Admin is registered successfully | Fail
|  | TC_004 | Register with missing mandatory fields |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "12345" into "Password*" 5. Select Role "Admin" 6. Click Register Button | Enter "vikas sahani" into "Name*" Enter "12345" into "Password*" Select Role "Admin" | Error message shows fill the input form | As Expected | Pass
|  | TC_005 | Register a Admin with invalid Password format |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "1" into "Password*" 6. Select Role "Admin" 7. Click Register Button | Enter "vikas sahani" into "Name*" Enter "vikas1@gmail.com" into "Email*" Enter "1" into "Password*" Select Role "Admin" | Enter the valid password | Admin is registered successfully | Fail
|  | TC_006 | Register a Admin with invalid Name format |  | 1. Open website 2. Click on "Sign Up" 3. Enter "1" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "1" into "Password*" 6. Select Role "Admin" 7. Click Register Button | Enter "1" into "Name*" Enter "vikas1@gmail.com" into "Email*" Enter "1" into "Password*" Select Role "Admin" | Give an error message | Admin is registered successfully | Fail

## Admin Login
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-Conditions | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_004 | Validate the 'Admin Login' functionality | TC_001 | Validater Admin Login with valid credentials | 1.Good internet 2.Laptop 3.URL : - https://pay-pal-pioneers-068.vercel.app/ 4.Browser :- Chrome-131 5.Admin on the Login page | 1. Open website 2. Click on "Login" 3. Enter the data | Enter "vikas1@gmail.com" into "Email*" Enter "12345" into "Password*" | Admin login successfully | As Expected | Pass
|  | TC_002 | Validater Admin Login with invalid credentials |  | 1. Open website 2. Click on "Login" 3. Enter the data | Enter "vikas1@gmail.com" into "Email*" Enter "1ddd" into "Password*" | Admin unable to login | As Expected | Pass
|  | TC_003 | Validate Admin Login with blank fields |  | 1. Open website 2. Click on "Login" 3. Enter the data | NA | Error message show | As Expected | Pass
|  | TC_004 | Validate Admin Login without enter Password |  | 1. Open website 2. Click on "Login" 3. Enter the data | Enter "vikas1@gmail.com" into "Email*" | Error message show | As Expected | Pass
|  | TC_005 | Validate Admin Login without enter Email |  | 1. Open website 2. Click on "Login" 3. Enter the data | Enter "12345" into "Password*" | Error message show | As Expected | Pass

## Admin Dashboard
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-Conditions | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_005 | Validate the 'Admin Dashboard' functionality | TC_001 | Validate if the category dropdown works correctly. | 1.Good internet 2.Laptop 3.URL : - https://pay-pal-pioneers-068.vercel.app/ 4.Browser :- Chrome-131 5.Admin on the Login page | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "12345" into "Password*" 6. Select Role "Admin" 7. Click Register Button 8. And login | N/A | Dashboard page should be loaded, and the dropdown should be visible when we click | as expected | Pass
|  | TC_002 | Verify Product Count Display |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "12345" into "Password*" 6. Select Role "Admin" 7. Click Register Button 8. And login | N/A | Product count widget should be visible. | as expected | Pass
|  | TC_003 | Verify Search Functionality |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "12345" into "Password*" 6. Select Role "Admin" 7. Click Register Button 8. And login | N/A | Product count widget should be visible and whatever admin can search, graph should change according to it | as expected | Pass
|  | TC_004 | Verify Sidebar Navigation |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "12345" into "Password*" 6. Select Role "Admin" 7. Click Register Button 8. And login | N/A | Sidebar should be visible and Admin should able to click on each | as expected | Pass
|  | TC_005 | Verify Sidebar Working |  | 1. Open website 2. Click on "Sign Up" 3. Enter "vikas sahani" into "Name*" 4. Enter "vikas1@gmail.com" into "Email*" 5. Enter "12345" into "Password*" 6. Select Role "Admin" 7. Click Register Button 8. And login | N/A | Sidebar's each button is working properly | Sidebar not working properly and when we click on other things all the other bars have same data | Fail

## Search Functionality
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_006 | Validate the 'Search ' functionality | TC_001 | Validate searching for Product Name | https://pay-pal-pioneers-068.vercel.app/ | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the Login page | Chrome-131 | 1. Visit the URL 2. Cick on the Search box 3. Click on the Search icon | Enter: Sancerre Blanc | 1. Searched product should be displayed in the search results | As Expected | Pass
|  | TC_002 | Validate searching for Product Name which is not in the list |  |  |  | 1. Visit the URL 2. Cick on the Search box 3. Click on the Search icon | Enter : Old Monk | 1. 'There is no product that matches the search criteria' should be displayed in the Search Results page | It didn't display any error, it gives empty page | Fail
|  | TC_003 | Validate searching Product without any name |  |  |  | 1. Visit the URL 2. Cick on the Search box 3. Click on the Search icon | N/A | 1.'There is no product that matches the search criteria' should be displayed in the Search Results page | There is no response from the search functionality,It didnt give any message | Fail
|  | TC_004 | Validate the suggestion of the product when enter the starting later |  |  |  | 1. Visit the URL 2. Cick on the Search box 3. Click on the Search icon | N/A | suggested product list should be displayed when user enters single letter in the search box | As Expected | Pass
|  | TC_005 | Verify that user is able to get search result when enters combination of alpha special characters |  |  |  | 1. Visit the URL 2. Cick on the Search box 3. Click on the Search icon | "Wine2024" | system should return search results related to "Wine2024", either a specific product or relevant content | As Expected | Pass
|  | TC_006 | Verify that user is able to enters with Special Characters |  |  |  | 1. Visit the URL 2. Cick on the Search box 3. Click on the Search icon | @wine# | System should either return results that match the special characters in the search term or display a no results message | As Expected | Pass
|  | TC_007 | Search with Alphanumeric and Special Characters Combined |  |  |  |  | Wine@123# | System should return relevant results containing products or content related to "Wine@123#". | As Expected | Pass
|  | TC_008 | Verify the Red wine in search functionality |  |  |  |  | Product Name : Red Wine | It shows the red wine products | As Expected | Pass

## Cart
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-Conditions | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_007 | Validate the 'Cart' functionality | TC_001 | Verify that the shopping cart icon is displayed as expected or not | 1.Good internet 2.Laptop 3.URL : - https://pay-pal-pioneers-068.vercel.app/ 4.Browser :- Chrome-131 5.User on the Login page | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | shopping cart icon is displayed as expected | As expected | Pass | N/A
|  | TC_002 | Verify that the shopping cart icon is clickable or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option | N/A | shopping cart icon is clickable | As expected | Pass | N/A
|  | TC_003 | Verify that the user is able to add items into the cart or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user is able to add items into the cart | As expected | Pass | N/A
|  | TC_004 | Verify if the user increase the number of items then the cart should be reflected as per qunatities |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user increase the number of items then the cart should be reflected as per qunatities | As expected | Pass | N/A
|  | TC_005 | Verify if the user decreases the items the number of items then the cart should be reflected as per quantities |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user decreases the items the number of items then the cart should be reflected as per quantities | Decreasing item quantity in the cart does not update the cart correctly. | Fail | N/A
|  | TC_006 | Verify that the user is click on the cart icon button then the user should navigate to the shopping cart page |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user is click on the cart icon button then the user should navigate to the shopping cart page | As expected | Pass | N/A
|  | TC_007 | Verify that the user is able to remove the products from the cart |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user is able to remove the products from the cart | As expected | Pass | N/A
|  | TC_008 | Verify that the total price should be corrected |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | total price should be corrected | As expected | Pass | N/A
|  | TC_009 | Verify that checkout option should be working properly |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | proceed checkout option should be working properlyVerify if the user removes all items from the cart,the cart should be displayed as empty | As expected | Pass | N/A
|  | TC_010 | Verify if the user removes all items from the cart,the cart should be displayed as empty |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user removes all items from the cart,the cart should be displayed as empty | As expected | Pass | N/A

## Checkout
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-Conditions | Test-Steps | Test Data | Expected Result | Actual Result | Status
TS_008 | Validate the 'Checkout' functionality | TC_001 | Verify that the user can proceed to checkout from the cart. | 1.Good internet 2.Laptop 3.URL :- https://pay-pal-pioneers-068.vercel.app/ 4.Browser :- Chrome-131 5.User on the Login page | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart | N/A | The user should be redirected to the checkout page from the cart. | As Expected | Pass
|  | TC_002 | Verify that the checkout page displays the correct product details. |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart | N/A | The checkout page should display the correct product name, price, quantity, and total cost. | As Expected | Pass
|  | TC_003 | Verify that enter the address in new customer option is taken or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option and enter the name,number, email | N/A | enter the address in new customer option is taken | As Expected | Pass
|  | TC_004 | Verify that User is able to enter the numbers in "Name" field in the address form |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | It shows an error " enter the name" | User is able to enter numbers in the "Name" field in the address form. | Fail
|  | TC_005 | Verify that enter the invalid number in address |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | It shows an error " enter the valid mobile number" | Checkoutf accepts the invlalid mobile number | Fail
|  | TC_006 | Verify that enter the invalid email in address |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | It shows an error " enter the valid email" | Checkout accepts the invlalid email | Fail
|  | TC_007 | Verify that i have an account option in checkout page open or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | i have an account option in checkout page open | As Expected | Pass
|  | TC_008 | Verify that it shows the saved address in checkout option or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | it shows the saved address in checkout option | It doent't show the saved address | Fail
|  | TC_009 | Verify that the user can enter and select a valid shipping address. |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | The valid shipping address should be entered and displayed correctly on the checkout page. | The valid shipping address should be entered and displayed correctly on the checkout page. | Pass
|  | TC_010 | Verify that the user can enter invalid shipping address. |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | It shows error"enter the valid address,mobile,email" | It accepts the invalid addres and proceed to checkout the payment | Fail
|  | TC_011 | Verify that enter the invalid current address |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | It shows error"enter the valid current address" | It accepts the invalid current addres and proceed to checkout the payment | Fail
|  | TC_012 | Verify that enter the numbers instead of giving characters in city name option |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | City : 1100 | It shows error"enter the city name" | The "City" field accepts numeric values, which should only accept alphabetic characters. | Fail
|  | TC_013 | Verify that enter the numbers instead of giving characters in state name option |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | State : 510 | It shows error"enter the state name" | The "State" field accepts numeric values, which should only accept alphabetic characters. | Fail
|  | TC_014 | Verify that enter the numbers instead of giving characters in district name option |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Dstrict : 852 | It shows error"enter the district name" | The "District" field accepts numeric values, which should only accept alphabetic characters. | Fail
|  | TC_015 | Verify that enter the invalid pincode |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Pincode : 963 | It shows error"enter the valid pincode" | The "Pincode" field accepts invalid pincode | Fail
|  | TC_016 | Verify that online payment method is selecting or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | online payment method is selecting | As Expected | Pass
|  | TC_017 | Verify that online payment upon receipt method is selecting or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | online payment upon receipt method is selecting | As Expected | Pass
|  | TC_018 | verify that continue the payment button work or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | continue the payment button is work | As Expected | Pass
|  | TC_019 | Verify that payment is successfull or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | payment is successfull | As Expected | Pass
|  | TC_020 | verify that user receives purchage message or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | user receives the thankyou for your purchage message | As Expected | Pass
|  | TC_021 | verify that user receives the email confirmation message or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | user receives the emaiol confirmation message | User didn't receive any email after completing the checkout process | Fail
|  | TC_022 | Verify that user enters the valid credentials in shipping and payment method |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | User successfully proceed with the payment | User successfully proceed with the payment | Pass

## Product Page
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_009 | Validate the 'Product P' functionality | TC_001 | Validate product name is not empty | https://pay-pal-pioneers-068.vercel.app/ | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the Login page | Chrome-131 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section | N/A | All products should have a visible and non-empty name. | All products should have a visible and non-empty name. | Pass
|  | TC_002 | Validate product price is displayed |  |  |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section | N/A | All products should have a visible and non-empty price. | All products should have a visible and non-empty price. | Pass
|  | TC_003 | Validate product rating is displayed |  |  |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section | N/A | All products should have a visible and non-empty rating. | All products should have a visible and non-empty rating. | Pass
|  | TC_004 | Validate all product details (name, price, rating) |  |  |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section | N/A | All products should display valid details for name, price, and rating. | All products should display valid details for name, price, and rating. | Pass
|  | TC_005 | Validate specific product details |  |  |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section | N/A | The product should match the expected name, price, and rating. | The product should match the expected name, price, and rating. | Pass

## Catlog Filter and Shorting
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-Conditions | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_010 | Validate the 'Catlog Filter and Shorting' functionality | TC_001 | Verify that selecting the All option in category is working or not | 1.Good internet 2.Laptop 3.URL :- https://pay-pal-pioneers-068.vercel.app/ 4.Browser :- Chrome-131 5.User on the Login page | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select All product option in price | N/A | selecting the All option in category is working | As Expected | Pass
|  | TC_002 | Verify that selecting the White wine in category |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select White wine product option in category | N/A | It shows only white wine products | Category option shows sprankling products instead of white wine products | Fail
|  | TC_003 | Verify that selecting the Red wine in category |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select Red wine wine product option in category | N/A | It shows only Red wine products | As Expected | Pass
|  | TC_004 | Verify that selecting the Rose wine in category |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select Rose wine wine product option in category | N/A | It shows only Rose wine products | Category Option shows sprankling products instead of Rose wine products | Fail
|  | TC_005 | Verify that selecting the wine sets in category |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select wine sets product option in category | N/A | It shows only Wine Sets products | Category Option shows sprankling products | Pass
|  | TC_006 | Verify that selecting the All option in price |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select All product option in category | N/A | selecting the All option in price is working | As Expected | Pass
|  | TC_007 | Verify that selecting the price between the 0$-50$ |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select price range option in Price | N/A | It shows only 0$-50$ products | As Expected | Pass
|  | TC_008 | Verify that selecting the price between the 50$-100$ |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select price range option in Price | N/A | It shows only 50$-100$ products | As Expected | Pass
|  | TC_009 | Verify that selecting the price between the 100$-150$ |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select price range option in Price | N/A | It shows only 100$-150% products | As Expected | Pass
|  | TC_010 | Verify that selecting the price between the 150$ above |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select price range option in Price | N/A | It shows only 150% Above products | As Expected | Pass
|  | TC_011 | Verify that selecting the All option in colors |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select All product option in colors | N/A | selecting the All option in colors is working | As Expected | Pass
|  | TC_012 | Verify that selecting the Sparkling color |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select sparlkilng color | N/A | It shows the sparkling color | As Expected | Pass
|  | TC_013 | Verify that selecting the white color |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select white color | N/A | It shows the white color | As Expected | Pass
|  | TC_014 | Verify that selecting the red color |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select red color | N/A | It shows the red color | As Expected | Pass

## Wishlist functionality
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-Conditions | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_011 | Validate the 'Wishlist' functionality | TC_001 | Verify that a user can add a product to the wishlist. | 1.Good internet 2.Laptop 3.URL :- https://pay-pal-pioneers-068.vercel.app/ 4.Browser :- Chrome-131 5.User on the Login page | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | N/A | The product should be added to the Wishlist. | As expected | Pass | N/A
|  | TC_002 | Verify that a user can view the wishlist. |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | N/A | The Wishlist should display the added products correctly with details like product name, image, price, and quantity. | The Wishlist should display the added products correctly with details like product name, image, price, and quantity. | Pass | N/A
|  | TC_003 | Verify if the user removes the item from the wishlist,the wishlist should be updated or not |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | N/A | User removes the item from the wishlist,the wishlist should be updated | User removes the item from the wishlist,the wishlist should be updated | Pass | N/A
|  | TC_004 | Verify that a user receives a confirmation message when adding a product to the wishlist. |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | N/A | A confirmation message should appear indicating that the product has been successfully added to the wishlist. | As expected | Pass | N/A
|  | TC_005 | Verify that the user can add products to the wishlist from the product listing page. |  | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | N/A | the product should be added to the wishlist, and the wishlist count should be updated. | the product should be added to the wishlist, and the wishlist count should be updated. | Pass | N/A

## UI and Non-Functionality testin
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-Conditions | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_012 | Validate UI and Non-Functionality testing | TC_001 | Check website loading speed (Performance) | 1.Good internet 2.Laptop 3.URL :- https://pay-pal-pioneers-068.vercel.app/ 4.Browser :- Chrome-131 5.User on the Login page | 1. Open the website in a browser. 2. Measure the time taken for the page to load fully. | N/A | The website should load in less than 3 seconds for a smooth user experience. | As Expected | Pass
|  | TC_002 | Test mobile responsiveness (Cross-Browser) |  | 1. Open the website in Chrome, Firefox, Safari, and Edge on mobile. 2. Ensure proper layout rendering and functionality. | N/A | The website should be properly displayed and functional on all mobile browsers. | As Expected | Pass
|  | TC_003 | Verify error messages are displayed correctly |  | 1.Enter invalid data in the form 2.Submit the form 3. Verify Error Messages | N/A | Verify error messages are displayed correctly | As Expected | Pass
|  | TC_004 | Verify if the page layout is responsive on desktop |  | 1. Open the website on a desktop | N/A | The layout should be responsive on desktop | As Expected | Pass
|  | TC_005 | Verify if the page layout is responsive on tablet |  | 1. Open the website on a tablet | N/A | The layout should be responsive on tablet | As Expected | Pass
|  | TC_006 | Verify if the page layout is responsive on mobile |  | 1. Open the website on a mobile | N/A | The layout should be responsive on mobile | As Expected | Pass
|  | TC_007 | Validate that the "Returns and Exchange" button is visible and clickable |  | 1. Open the website in a browser. 2. Go to the footer links. | N/A | "Returns and Exchange" should be visible and clickable | As Expected | Pass
|  | TC_008 | Verify that only one payment option (Online Payment or Payment Upon Receipt) can be selected at a time |  | 1. Open the website in a browser. 2. Go to the checkout | N/A | Only one radio button should be selected at a time. If "Payment Upon Receipt" is selected, "Online Payment" should be unselected. | Both radio buttons 'Payment Upon Receipt' and 'Online Payment' can be selected simultaneously, but only one should be selected at a time. | Fail
|  | TC_009 | Verify if the website works conrrectly on multiple browsers |  | 1. Open the website in Chrome, Firefox, Safari, and Edge on desktop. 2. check if the browser works properly | N/A | The wesite should works properly in every browser | As Expected | Pass
|  | TC_010 | Verify the visibility of radio buttons for filters and sorting |  | 1. Navigate to the filters and sorting options. 2. Ensure radio buttons are clearly visible. | N/A | The radio buttons should have enough contrast to stand out from the background and be easily visible. | The radio buttons lack sufficient contrast against the background, making them difficult to see | Fail